Minutes for Opening meeting November 28 and 29 2007.

Present:

Jean Claude Arnaud (USEP),

Iztok Retar (SUS),

Anders Kragh (DGI),

Paolo (UISP),

Loredana (UISP),

Marvin Radford (ISCA),

Mette Ravn (ISCA).

The meeting was held in DGI-byen in Copenhagen.

1. Welcome and presentation of programme /ISCA

2. Presentation of associate partner’s own health programmes and initiatives.

PP presentations attached

3. Presentation of PATHE objectives /ISCA

As they appear in the project description.

It was remarked that it has been more than 18 months since the initial proposal was made and that the circumstances for the partners in that period has changed, making some of the originally planned elements outdated. For the parts were changes are necessary compared to the original project description, updates should be sent to ISCA before December 15.

4. Presentation of PATHE mile stones and work packages /ISCA

WP3 (Evaluation) is handled by UISP see attached.

5. Twinnings and consultations – how, when and (by) who /All partners

- Agreement to send to collaborating partners is to be elaborated by ISCA. Should describe what are the gains and costs of participating.

- ISCA to explore if twinnings can be held simultaneously.

- Associate partners to send suggestions for new collaborating partners by December 15.

6. Fixing the PATHE calendar /All partners

- Calendar task cannot be handled by www.timeanddate.com but will be on www.isca-web.org instead.

7. Financing PATHE /ISCA

- Associate partner input: salary of employees and already planned and financed activities.

- ISCA will investigate if and how voluntary work can be part of own-financing.

8. Summarising what has been achieved and what needs clarification/ISCA

- Logo for PATHE to be prepared by USEP. Log should be used on all documentation.

- Electronic time sheet attached